## Sheet1
Ground Up Development Checklists | Legend: | (white) not started | (yellow) in progress | (green) complete or N/A
| Project 1 | Project 2 | Project 3 | Project 4
After LOI is Executed
Get seller/landlord deliverables: survey, title, geotech, environmental, tax records
Ensure land is not in flood plain
assemble preliminary develoment budget
get civil engineer proposal
ensure civil includes as-built survey in services
get architect proposal
assemble preliminary development schedule
Ensure legal council has started on initial draft of land PSA/ground lease and follow up weekly
After initial draft of lease/PSA is out for distribution, drive the negotiation process forward by periodically following up with all parties on status of their review and comments
Release architect on: Site Investigation Survey, CSP, elevations, rendering
Have civil investigate need for onsite detention and share with architect for site plan
Get client approval of CSP/elevations/rendering before putting in lease/PSA
Schedule pre-development meeting with city
Ask questions from “City Pre-Development Meeting Questions” list
After pre-development meeting with city, update project schedule and share with whole project team
Get civil to validate all utilities are at pad site and have sufficent capacity. If not, negotiate in the ground lease/PSA that LL/seller brings to pad site and upsizes capacity.
After land PSA/ground lease is executed
Order geotech
Order Environmental Phase I Report. Make sure liability coverage is more than just fee amount for report.
Order Phase II (if necessary)
Order asbestos survey (if necessary)
Execute civil enigneer contract
Execute architect contract
Get a zoning verification letter from city
Ensure legal council orders and reviews title
Order ALTA Survey (add topo if necessary)
Put IP & AP expiration on Critical Dates List and put on task list to remind client of expiration a week prior
Get bank's loan closing checklist
Send architect, structural, civil & GC geotech report
Get utility will-serve letters
If P&Z/City Council approval required for entitlement, meet with members before hearing to pre-sell
Before plans are released for bid and permit
Schedule 95% owner review of plans before release for bid & permit
If a mockup is a good idea for this project, make sure architect puts in plans
Ensure client relaizes they are respobsible for FF&E and signage. Share with them recommended vendors (cabling, furnitrure, moving)
Get with client’s IT staff to properly define the scope of work so that IT vendors can price accurately
Have a pre-bid meeting onsite with the bidding GCs
If a P&P bond is required, have the GC include in bid
Ask owner if he wants a monument sign and if so, where, how big and what should it look like.
Call city to understand what submission requirement are for permit and fill out forms/assemble permit submission package
After Plans are Ready for Bid & Permit
Submit plans for permit to city
send plans to CMT company to get proposal
Send building plans to ground lease LL for his review and approval (if applicable)
Send plans out for bid
Level bids and present recommendation to client
Whenever I do something noteworthy, write it in the comments of this cell so I have material for my LOR
Inform tenant's GC (if any) of LL required subs (controls, fire alarm, etc.)
Congradulate and issue notice to proceed to winning GC
Have tenant sign off on plans
Debrief losing GC bidders
After Construction Contract is Awarded
Set up plan review between architect, GC and major subs to ensure pre-construction questions are answered
Execute constuction contract with GC
Make GC aware of CMT requirements
Have the GC pursue a demo, grading and/or foundation permit if it will allows us to get a head start on the project ahead of the building permit
Tell the GC to start pre-construction based on the LOI/NTP: buy out subs, start on steel shops, order long lead time equipment, start on submittals
Have the GC order the electrical service transformer and gas meter early
During Construction
Set up recurring OAC meetings
Have any specialty equipment vendors validate construction rough-in (if needed) e.g. signage, medical equip
Remind tenant to get FF&E and signage vendors engaged so they can install immediately after construction completion.
Have GC lay out walls in chalk and invite client(s) to walk space before erecting walls
If any construction rough-in or blocking is required for FF&E or signage, coordinate it.
Schedule installation of “Coming Soon” sign with signage vendor
At OAC meetings, take photo notes (Site Audit Pro) of issues and review them at the following meeting
Put on task list to send client bi-weekly updates during construction (send pics)
Store all pay apps and change orders to share drive and organize them
Ensure structural engineer walks site after misc steel is in place, but before covering up, to verify structure is built to plans
Walk wall rough in to verify MEP placement before closing up walls
Schedule 50% construciton completion walk thru with client
Ensure signage vendor visits jobsite to ensure blocking and electrical whips are in the proper location.
Ask tenant how they want all locks keyed. This will be a change order to the tenant or project.
For repetative rooms like exam or resident rooms, make sure all outlets, switches, and drainlines are uniformly in the same spot on the wall
Near end of construction
Start reviewing transition checklist from development to property management
Ask GC to start assembling closeout documents
Schedule punch list walk (invite cliet)
Have the superintendent find out the exact procedures to get Cert of Occupancy and brief me on it
Lock in a Cert of Occupancy receipt date from GC and share with client
Get ready to switch over from consturction insurance to property insurance after CO
Ensure property management is aware of move in date and prepares: keying, door signage, AOP, move-in packet, tenant COI (Cc client on email)
After Construction Completion
Plan to show up on client move day for face time (if client will be there)
Reconcile construction allowances
Have civil engineer do as-built ALTA survey
Schedule ADA/TAS inspection
Have architect do up Cert of Substantial Completion
Deliver a gift to the client at move-in
Ensure all Close-out docs are collected
As-builts drawings
All Permits
Certificate of Occupancy
Final unconditional lein waivers from GC and subs
Punch list and punch list completion validation signed by architect
Test & Balance Report
Fire-Lie Safety inspection report
Backflow test report
O&M manuals
Department of Health final inspection documents
Paint color list
Contact list of subcontractors
1 year warrantee letter from GC and subs
25-year Roof warrantee
Receive and review ADA/TAS insection
Email full closeout docs to Owner and Property Management
Send out calendar invite for 11-month warrantee walk
Ask client for a Letter of Recommendation based on my performance
Note on A6: https://msc.fema.gov/portal/search and just type in the address or place. You can then download or screen shot the map
Note on A37: Suitonu, Chad: Take 11 x 17 bounded copies of the plans for each client Make sure I review these plans before I meet with the client Colorcode the supply and return ducts on the HVAC plan Color circle where all the tstats are and show what VAV they control and what zone
Note on A58: Chad Suitonu: OAC meeting requirements -submittal log -issues log -RFI log -change order log -updated schedule -progress photos -pre-con meeting requirements -weather delay days CMT requirements Liquidated Damages Closeout documnets requirements
Note on A93: Chad Suitonu: donuts and coffee at office set up deliver in person staple card to donut box so everyone knows who it is from
Note on A112: Chad Suitonu: review project emails to jot my memory on noteworthy things I did Keep track of every dollar I save the owner make a spreadsheet showing the difference between CORs submitted and CORs approved If there is a change order that the owner should have been charged, but i got the GC to take care of it, let the owner know. Schedule compression If there was money saved from compressing schedule, include that Competitive bidding process Note the difference between the average bid and the low bid Through my knowledge and relationships with GCs, I knew which ones to invite that would give competitive pricing Scope reduction of unneeded items Ask the client if he really needs something or if he picks something expensive, inform him of the costs of that item Control overdesign by the architect As I review the plans, if I know of a cheaper way to do something, mention it to the architect and owner Value Engineering The difference between change orders submitted and change orders approved
Note on B9: Chad Suitonu: not in proposal, but included per email from Ray on 11/5/21 Chad, The Civil bill will be $86,800. This includes an ALTA survey, topographic survey, As-Built survey, staking of lot and building corners, the civil site plan, preliminary plat, final plat and monthly site visits. I have also included City fees associated with the platting and site plan review. • The price does not include the ADA review fee because I am assuming the architect will include that in their pricing. • The price does not include the building permit, construction staking or SWPPP, because I am assuming that the contractor will include these items in their pricing. Ray M. Bridges, P.E. Urban Engineering 2004 N. Commerce St Victoria, TX 77901 (361) 578-9836 www.urbanvictoria.com