## Detail on pre-dev costs
Loan/Land Closing
| Sep '21 | Oct '21 | Nov '21 | Dec '21 | Jan '21 | Feb '21 | Mar '21 | Apr '21 | May '21
Land Purchase
Initial Earnest Money | 50000
Additional earnest money |  |  | 50000
Arch Design
Conceptual Plans |  | 10000
Schematic Design |  |  | 184500 | 184500
Design Development |  |  |  |  | 184500 | 184500
Construction Documents | [6 empty] | 246000 | 246000
Landscape Design
Conceptual plan & narrative for pricing |  |  | 5000
Landscape design |  |  |  | 20000 |  | 20000
Interior Design |  |  |  | 16000 | 16000 | 16000 | 16000 | 16000
Kitchen/Laundry Design |  |  |  |  | 5000 | 10000 | 10000 | 10000
Civil Design
Prelim site plan |  | 8000
ALTA survey w/ topo |  |  | 9500
Utility cooridnation
Civil Plans |  |  |  | 24000 | 24000
Misc services |  |  | 2500 | 8000 | 2500 | 3000
Consultants | [6 empty] | 25000
TDADAs Consultant | [7 empty] | 13000
Geotech Survey |  |  |  | 12000
Environmental Survey |  | 1800
Travel |  | 500 | 500 | 500 | 500 | 500 | 500 | 500
Legal Fees
Land Purchase |  | 15000
Titel review |  |  | 5000
Development agreement |  |  |  |  | 10000
LP agreement |  |  |  |  | 10000
Lender docs | [5 empty] | 5000 | 10000
Misc
Contingency
JLL market study | 10000
City fees |  |  | 5000 |  |  | 10000
Total: | 60000 | 35300 | 262000 | 265000 | 252500 | 249000 | 307500 | 285500 | 0 | 1716800 | Grand Total Pre-Development Costs