## Responsibility Matrix
[Project Name] Senior Living Community Responsibility List*
*This list is not meant to be all inclusive, but only clarifies responsibilities which may be confusing.
List of Responsible Party Members
Owner | Low Voltage Contractor | Landscape Architect
Architect | Operator | Civil Engineer
General Contractor | Interior Designer | Pool subcontractor
Structural Engineer | MEP Engineer | Exterior Signage Contractor
Interior Signage Contractor | Foodservice Contractor | Home Builder
Responsible Party | Task
Pre-Design
Architect | Programming
Operator | Programming assist
Owner | Project Budget
Operator | Operational Proforma
Owner | ALTA Survey
Owner | Environmental Survey
Owner | Geotech Report
N/A for this project | Traffic Impact Analysis (if required)
Architect | Concept Site Plan Test Fit
Civil Engineer | Assist Owner with entitlement and platting of land
Site Design
Earthwork
Civil Engineer | SWPPP plan - design
Civil Engineer | Site Grading - design
Landscape Architect | Aesthetic Grading - design
Utilities
Civil Engineer | Utility Plan
Civil Engineer | Gas before meter - design
Civil Engineer | Irrigation sleeves under pavement - design
Civil Engineer | Drainage/storm water and detention plan
MEP Engineer | Backflow preventer for domestic water and irrigation system
MEP Engineer | Hose Bibs Design & Placement
MEP Engineer | Gas after meter
MEP Engineer | Domestic water distribution
Paving
Architect | Conceptual Parking Layout
Operator | Input on carport and garage parking counts
Civil Engineer | Final site plan (showing all paving)
Civil Engineer | Paving Design
Civil Engineer | Retaining wall need identification
Structural Engineer | Retaining Wall Design
Landscaping
Landscape Architect | Schematic landscape budget
Landscape Architect | Hardscape, Flatwork - design
Landscape Architect | Hardscape, Vertical Features - design
Landscape Architect | Courtyards - design
Landscape Architect | Recreational amenities (tennis courts, bocce ball, putting greens, etc) layout
Structural Engineer | Foundations & structural concrete for recreational amenities
Landscape Architect | Planting Design
Landscape Architect | Landscape & Hardscape fixtures (e.g. fixed benches) - design/selection
Landscape Architect | Large exterior planters - design/selection
Landscape Architect | Landscape Plan
Landscape Architect | Irrigation system schematic design
General Contractor | Irrigation system design/build
Landscape Architect | Landscape & hardscape lighting - design
MEP Engineer | Landscape & hardscape lighting - electrical power coordination
Landscape Architect | Water features - design
MEP Engineer | Water features - water supply and drain coordination
Landscape Architect | Exercise/Nature Trail design
Landscape Architect | Site Furnishings (e.g. benches along trail) design/selection
Landscape Architect | Boulevard entry feature (e.g. fountain or statue)
Landscape Architect | Drop-off Entry feature (e.g. fountain or statue)
Landscape Architect | Outdoor kitchen/grill area - design
MEP Engineer | Outdoor kitchen/grill area - MEP supply coordination
Landscape Architect | Exterior fire place/fire pit - design
MEP Engineer | Exterior fire place/fire pit - MEP supply coordination
Pool
Landscape Architect | Outdoor pool concept design
Landscape Architect | Concept outdoor pool deck and surrounding hardscape
Pool subcontractor | Final pool design/build
Pool subcontractor | Pool deck system drain to storm water system
MEP Engineer | Domestic water supply to pool
MEP Engineer | Pool system electrical panels and disconnect
MEP Engineer | Pool system drain to storm water system
N/A for this project | Indoor pool design (if any)
Signage
Landscape Architect | Monument and wayfinding signage concept
Exterior Signage Contractor | Monument, Wayfinding & Building Exterior Signage Design-Build & install
Exterior Signage Contractor | Signage along nature trail
MEP Engineer | Electrical supply to exterior illuminated signs - design
General Contractor | Electrical supply to exterior illuminated signs - furnish & install
Misc. Site
Architect | Flagpole Design
Operator | Select furnish & install flags
Architect | Bike rack design and selection
General Contractor | Furnish & install bike racks
Architect | Exterior trash receptacle design and selection
General Contractor | Exterior trash receptacle furnish & install
Building Core & Shell Design
MEP Engineer | Building exterior lighting design
MEP Engineer | Site lighting design
Architect | Site fixture selection
MEP Engineer | Schematic Design bid package MEP narrative
MEP Engineer | Overall final MEP design
Architect | Elevator selection
Interior Designer | Elevator cab finishes selection
Architect | Trash closets/chutes design
Architect | Drop-off Entry (e.g. porte cochere)
Structural Engineer | Schematic Design bid package structural narrative
Structural Engineer | Final Structural Design
Building Interiors Design
Lighting
Interior Designer | Decorative light fixture selection and plan
General Contractor | Furnish & install decorative lighting fixture package
Architect | Back of House (BOH) Light Fixture selection and plan
General Contractor | Furnish & install BOH lighting fixture package
Architect | Create lighting schedule to include all lights, decorative & BOH
MEP Engineer | Lighting controls design
Interior Designer | Lighting controls design assist
Interior Designer | Power & data outlet location coordination for FF&E
Signage
Architect | Code required interior signage - specify & design
General Contractor | Code required interior signage - furnish & install
Interior Designer | Interior wayfinding sign concept plan
Interior Signage Contractor | Interior wayfinding and room signs - design, furnish & install
Interior Signage Contractor | Interior marketing signage - design, furnish & install
Finishes
Interior Designer | Common area finishes selection
Interior Designer | Common area finishes schedule
Interior Designer | Unit finishes selection
Interior Designer | Unit finishes schedule
Interior Designer | Paint & wall covering selection
Interior Designer | Back of house finishes
Interior Designer | Ceiling concept design
Architect | Reflective ceiling plan
Architect | Toilet accessories selection - common area & units
Interior Designer | Toilet accessories input - common area & units
Interior Details
Interior Designer | Interior elevations
Interior Designer | Interior details
Interior Designer | Common area built-in millwork design
Architect | Back of house built-in millwork design
Architect | Units built-in millwork design
Doors & Windows
Architect | Door and hardware schedule
Architect | Door finish selection
Interior Designer | Door finish input
Architect | Door hardware selection
Interior Designer | Door hardware input
Architect | Window schedule
Fixtures
Architect | Common restroom & unit bath plumbing fixture selection
Interior Designer | Common restroom & unit bath plumbing fixture input
Architect | Common restroom & unit bath plumbing fixture schedule in plans
General Contractor | Common restroom & unit bath plumbing fixture - furnish & install
Interior Designer | Fixed mirrors - selection
General Contractor | Fixed mirrors - furnish & install
Architect | Closet hardware design/selection
General Contractor | Closet hardware - furnish & install
Food Service
Foodservice Contractor | Kitchen design
Operator | Kitchen design input
Foodservice Contractor | Food service equipment group I (Hoods, walk-ins) - select
Operator | Food service equipment group I (Hoods, walk-ins) - input
General Contractor | Food service equipment group I (Hoods, walk-ins) - furnish & install
Foodservice Contractor | Food service equipment group II (Oven, dishwashers, ice makers) - select
General Contractor | Food service equipment group II (Oven, dishwashers, ice makers) - furnish & install
Operator | Food service equipment group II (Oven, dishwashers, ice makers) - input
Operator | Food service equipment group III (small wares) - select, furnish & install
Operator | Apply for food service permit
Misc.
Architect | Lockers design & selection
General Contractor | Lockers furnish & install
Architect | Corner guards design & selection
General Contractor | Corner guards furnish & install
Architect | Find out from local postmaster if mailboxes can be inside, or if they have to be outside.
N/A for this project | Dance floor (if any)
Architect | Mailboxes - design/selection
Architect | Fire extinguisher - selection & placement
Architect | Operable partitions - design/selection
Low Voltage Contractor | cabling j-boxes & conduit (if any)
N/A for this project | Acoustics design (if any)
FF&E
Interior Designer | Schematic FF&E budget
Interior Designer | Interior movable planters - select, furnish & install
Interior Designer | Interior plants - select, furnish & install
Interior Designer | Art - selection, furnish & install
Interior Designer | Window coverings, common area - select, furnish & install
Interior Designer | Window coverings, units - select
General Contractor | Window coverings, units - furnish & install
Interior Designer | Interior furniture - select, furnish & install
Interior Designer | Outdoor common area (patio,courtyard,balcony) furniture - select, furnish & install
Interior Designer | Theater chairs - select, furnish & install
Interior Designer | Beauty Salon/Spa chairs and FF&E - select, furnish & install
Operator | Beauty Salon/Spa chairs and FF&E - input
MEP Engineer | MEP connection coordination for salon chairs and FF&E
General Contractor | MEP connection for salon chairs and FF&E
Interior Designer | Beauty Salon/Spa interior design
Foodservice Contractor | Laundry equipment design
General Contractor | Laundry equipment furnish & install
Architect | Trash compactor design/selection (if any)
Architect | Unit appliances (refrigerators, ovens, dishwashers, etc.) - selection
Interior Designer | Unit appliances (refrigerators, ovens, dishwashers, etc.) - input
General Contractor | Unit appliances (refrigerators, ovens, dishwashers, etc.) - furnish & install
Architect | Employee breakroom appliances - selection
Interior Designer | Memory Care directional boxes selection, furnish & install
Operator | Arts & Crafts equipment - select, furnish & install
Operator | Athletic & Recreation equipment - select, furnish & install
Operator | Gym equipment - select, furnish & install
Operator | Game room equipment - select, furnish & install
Operator | Soap dispensers, hand sanitizers, sharps containers
Operator | Vending equipment
Operator | Entry mats
Interior Designer | Furnish model units
Operator | Staff computers - select, furnish & install
Operator | Copiers, Fax, Scanners, Printers - select, furnish & install
Operator | Mail room meter - select, furnish & install
Operator | Staff time & attendance system - select, furnish & install
Low Voltage
Operator | Surveillance equipment - selection & furnish
Low Voltage Contractor | Surveillance equipment - install
Low Voltage Contractor | Surveillance equipment wiring
Operator | Access control - ID doors to receive access control
Architect | Access control - design and hardware/system selection
Operator | Access control - input on design and hardware/system selection
General Contractor | Access control door hardware - furnish & install
Low Voltage Contractor | Access control - furnish & install card readers and head end system
Low Voltage Contractor | Access control - equipment wiring
Operator | Point of Sale system - selection
Operator | Point of Sale system - furnish and install
Low Voltage Contractor | Point of Sale system - low voltage wiring
Operator | Telephone system - selection
Operator | Telephone system - furnish & install
Low Voltage Contractor | Telephone wiring
Low Voltage Contractor | Data cabling
Low Voltage Contractor | Coax cabling
Interior Designer | Televisions & digital directories (Common area) - ID size & location
Operator | Televisions & digital directories (Common area) - furnish & install
Operator | Media room sound system - specify
Operator | Media room sound system - furnish & install
Low Voltage Contractor | Television cabling
General Contractor | Blocking for Televisions
Operator | Wi-Fi system (WAPS) - design & furnish
Low Voltage Contractor | Wi-Fi system (WAPS) - install
Operator | IT closet equipment (e.g. server, hub, modem) - design & selection
Operator | IT closet equipment (e.g. server, hub, modem) - furnish
Low Voltage Contractor | IT Equipment (e.g. server, hub, modem) - install
General Contractor | IT closet plywood on walls
Operator | Nurse call (Skynet fitbit type) - system selection/design and furnish
Low Voltage Contractor | Nurse call ceiling mounted sensors - install
Low Voltage Contractor | Nurse call ceiling mounted sensors - wiring
Operator | Hearing aid loop - design/selection and furnish
Low Voltage Contractor | Hearing aid loop - install
N/A for this project | Wander management system - selection, furnish & install
N/A for this project | PA system - selection, furnish & install
N/A for this project | Sound system - design, furnish & install
Pre-Construction
General Contractor | Submit plans for permit
General Contractor | Payment of all construction related permits
Owner | Payment of impact/meter/tap fees
General Contractor | Utility costs during construction
Construction
General Contractor | Builder's Risk Insurance
Owner | Construction Materials Testing
General Contractor | Earthwork survey/steakout
General Contractor | Form and slab survey
General Contractor | Fixed manufactured millwork - furnish & install
General Contractor | Electrical secondary service from transformer to meter
General Contractor | MEP as-built plans after construction completion
Civil Engineer | Provide as-built site survey after construction completion
IL Cottages/Townhomes (if any)
General Contractor | earthwork (final grading and compaction) of pad sites
General Contractor | stub out water & sewer utilities to individual pad sites
Home Builder | connect water & sewer utilities from stubouts to cottages/townhomes
General Contractor | curb cuts to individual pad sites
General Contractor | Sidewalks in front of cottages/townhomes
Home Builder | run electrical, gas, data/tele to individual homes
Home Builder | build cottages/townhomes
Facility Licensing
Architect | Submit plans for State licensing body review
Owner | Pay fee for review of plans by State licensing body
Facility Pre-Opening
N/A for this project | Furnish & install marketing trailer
Operator | lease nearby space for marketing office
Interior Designer | FF&E for marketing trailer/office
Operator | Select finishout and FF&E for marketing trailer/office - input
N/A for this project | Run utilities to marketing trailer (change order to Owner)
Operator | lease cars, buses, vans and/or golf carts for operations
General Contractor | Receipt & storage of small misc FF&E shipments
Interior Designer | unpacking and installation of FF&E

## Team Members
Team Members List
1 | Owner
2 | Architect
3 | General Contractor
4 | Low Voltage Contractor
5 | Operator
6 | Interior Designer
7 | Landscape Architect
8 | Civil Engineer
9 | Pool subcontractor
10 | Structural Engineer
11 | MEP Engineer
12 | Exterior Signage Contractor
13 | Interior Signage Contractor
14 | Foodservice Contractor
15 | Home Builder
16 | N/A for this project